## Summary
AI Mesh — GCP cutover issues tracker
Product: AI Mesh Firewall ¦ GCP project: aisecshield-prod ¦ Last verified: 23 Aug 2026 16:40 UTC ¦ Working owner: DevOps
Production traffic is still on AWS. This workbook tracks remaining open GCP / Cloudflare items only. Do not re-work rows on the Closed sheet. Update Status, Owner, and Target date on Open issues as work proceeds.
Snapshot
Metric | Value |  |  | Priority | Count
Open issues | 13 |  |  | Blocker | 3
Blockers (need a planned DNS window) | 3 — cert, Cloudflare two-IP plan, split-cert trap |  |  | High | 5
High — fix before names go public | 5 — Redis size, gateway timeout, SSH, leftover FW, ECR |  |  | Medium | 4
Medium | 4 |  |  | Info | 1
Info / expected until cert is ACTIVE | 1 — origin self-signed
Closed — verified, no action | 5
UI / API load-balancer IP | 34.110.253.110
Gateway SSL-proxy IP (NLB analogue) | 136.68.95.231
Origin IP (hosts-file testing only) | 34.14.209.218
DNS authority | Cloudflare (shubhi / tanner.ns.cloudflare.com) — not Route53
Cloudflare cutover (rollback = current AWS ELB CNAMEs)
DNS name | Target after cutover | Role | Do not point at
aimeshfirewall.zeroshield.ai | A 34.110.253.110 | UI (nginx HTTP/HTTPS LB) | Gateway SSL-proxy IP
aimeshbackend.zeroshield.ai | A 34.110.253.110 | Control API (same LB) | Gateway SSL-proxy IP
aimeshgateway.zeroshield.ai | A 136.68.95.231 | Inference gateway (SSL proxy → :8300) | 34.110.253.110 (nginx, not the NLB path)
Sheets
Open issues — working tracker (filters + drop-downs on Status / Priority). Fill Owner, Target date, Notes as you go. Closed — do not rework — items already verified live. Not issues — Redis generation / data / frontend parity; no ticket. Cutover checklist — before / during / after the Cloudflare window. Priority: Blocker = cannot flip DNS safely without a window or plan; High = fix before names are public; Medium = same programme; Info = expected until the Google cert is ACTIVE.

## Open issues
ID | Priority | Status | Category | Issue | Blocks DNS cutover? | Fix before public DNS? | Current state (verified 23 Aug 2026) | Required / expected | AWS comparison | Recommended action | Owner | Target date | Evidence / how to verify | Notes / last update
MESH-GCP-01 | Blocker | Open | Certificate | Google-managed cert is not ACTIVE — HTTPS to both public LBs fails | Yes | Yes (window) | mesh-firewall-cert status PROVISIONING; domainStatus FAILED_NOT_VISIBLE on aimeshfirewall, aimeshbackend, aimeshgateway. curl HTTPS to 34.110.253.110 and 136.68.95.231 → TLS unexpected EOF. No peer certificate. | Certificate ACTIVE on all three names; public HTTPS 200 with Google-managed cert (not self-signed). | ACM *.zeroshield.ai ISSUED (Amazon RSA 2048), NotAfter 2026-11-06/07, in use on ALB and NLB. | Plan a cutover window. Cert cannot become ACTIVE until public DNS points at the LB IPs. After the flip, HTTPS is down until Google issues the cert. Hosts-file testing must use 34.14.209.218, not the LB IPs. | DevOps |  | gcloud compute ssl-certificates describe mesh-firewall-cert --global --project=aisecshield-prod; curl -v --resolve aimeshfirewall.zeroshield.ai:443:34.110.253.110 https://aimeshfirewall.zeroshield.ai/login | Chicken-and-egg with DNS. Do not treat “cert not ACTIVE” as a GCP bug to force before DNS.
MESH-GCP-02 | Blocker | Open | DNS / Cloudflare | Cutover is Cloudflare (two IPs), not Route53 — gateway must not use the UI LB IP | Yes | Yes (window) | Apex NS shubhi/tanner.ns.cloudflare.com. Live records still CNAME to AWS ALB (firewall/backend) and AWS NLB (gateway). Route53 in 935951870001 has no zeroshield.ai zone. | Cloudflare A records: firewall+backend → 34.110.253.110; gateway → 136.68.95.231. Rollback = current ELB CNAMEs. | aimeshfirewall/backend → aimesh-firewall-alb-1475611690.ap-south-1.elb.amazonaws.com; aimeshgateway → aimesh-firewall-nlb-92c0d7669161363f.elb.ap-south-1.amazonaws.com | Document and execute Cloudflare change (not Route53). Do not point aimeshgateway at 34.110.253.110 (nginx path, not NLB-equivalent). | DevOps / DNS owner |  | dig NS zeroshield.ai; dig CNAME aimeshfirewall.zeroshield.ai aimeshbackend.zeroshield.ai aimeshgateway.zeroshield.ai; aws route53 list-hosted-zones | Pointing all three names at 34.110.253.110 is incorrect now that the gateway SSL proxy exists.
MESH-GCP-03 | Blocker | Open | Certificate architecture | One certificate (three SANs) attached to two different LB IPs — can keep cert in FAILED_NOT_VISIBLE | Yes | Yes (before or during window) | Same mesh-firewall-cert attached to mesh-firewall-https-proxy (34.110.253.110) and mesh-firewall-gateway-ssl-proxy (136.68.95.231). Google-managed certs require each SAN to resolve to an IP that presents that cert. | Either move all three names in one window to the correct IPs, or split certs: firewall+backend on HTTP(S) LB; gateway-only on SSL proxy. | ALB and NLB both use the same ACM *.zeroshield.ai wildcard (single SAN works on both IPs). | Prefer split certs before flip, or move all three Cloudflare records together. Confirm cert ACTIVE on every SAN after DNS. | DevOps |  | gcloud compute target-https-proxies describe mesh-firewall-https-proxy --global --project=aisecshield-prod; gcloud compute target-ssl-proxies describe mesh-firewall-gateway-ssl-proxy --project=aisecshield-prod | If only firewall/backend move, aimeshgateway can block the whole cert from becoming ACTIVE.
MESH-GCP-04 | High | Open | Redis / Memorystore | Memorystore is 1 GiB BASIC vs production ElastiCache ~26 GiB | No | Yes | mesh-firewall-redis: tier BASIC, memorySizeGb 1, Redis 7.2, AUTH unset, transitEncryptionMode DISABLED, persistence DISABLED. App REDIS_URL=redis://10.19.125.51:6379/0 (PONG). | Capacity comparable to production (or a written acceptance of 1 GiB risk). AUTH/TLS still off on AWS too — capacity is the mismatch. | ElastiCache aimesh-redis cache.r7g.xlarge (~26 GiB), Redis 7.1.0, AUTH off, at-rest/transit off, snapshot retention 0. | Resize Memorystore before traffic moves. Policy count is already 246 on both sides — this is not a missing dump. | DevOps |  | gcloud redis instances describe mesh-firewall-redis --region=asia-south1 --project=aisecshield-prod | Hot policy/session working set that fits in 26 GiB can evict or pressure 1 GiB after cutover.
MESH-GCP-05 | High | Open | NLB / gateway timeout | Gateway TCP backend timeout is 30s (AWS NLB idle is 350s) | No | Yes | mesh-firewall-gateway-backend protocol TCP, portName gateway, timeoutSec 30. Backend health HEALTHY on :8300. nginx proxy_read_timeout for /v1/ is 360s (UI host only). | timeoutSec at least 60s; 300–350s to match current NLB streaming/SSE behaviour. | NLB TLS 443 → target :8300; TCP idle timeout default 350s. ALB idle 60s (UI/API GCP backend already 60s — closed). | Raise mesh-firewall-gateway-backend timeout (prefer 350). Do not change UI/API mesh-firewall-backend (already 60s). | DevOps |  | gcloud compute backend-services describe mesh-firewall-gateway-backend --global --project=aisecshield-prod --format="yaml(timeoutSec,protocol,portName)" | UI/API timeout is already 60. This ticket is gateway-only.
MESH-GCP-06 | Medium | Open | TLS policy | SSL policy attached but weaker than AWS TLS 1.3 + post-quantum | No | No | mesh-firewall-ssl-policy profile MODERN, minTlsVersion TLS_1_2, attached to HTTPS proxy and gateway SSL proxy. No post-quantum field. Cipher set is TLS 1.2 ECDHE AES/CHACHA. | Align toward TLS 1.3-restricted + PQ comparable to ELBSecurityPolicy-TLS13-1-2-Res-PQ-2025-09. | ALB/NLB SslPolicy ELBSecurityPolicy-TLS13-1-2-Res-PQ-2025-09. | Update ssl policy (or custom features) so public TLS posture does not regress after cutover. | DevOps |  | gcloud compute ssl-policies describe mesh-firewall-ssl-policy --project=aisecshield-prod | Previous “no SSL policy” finding is closed. This is residual alignment only.
MESH-GCP-07 | High | Open | Firewall / SSH | SSH is still world-open (tcp/22 0.0.0.0/0) | No | Yes | cyberultron-aisecshield-vpc-allow-ssh and default-allow-ssh: tcp/22 from 0.0.0.0/0. Proven open from the AWS instance. UFW inactive on the VM. | SSH limited to operator IPs: 8.231.115.48/32, 103.212.146.96/32, 157.49.179.163/32 (same as AWS). | Instance SG SSH only those three /32s. | Restrict both VPC SSH rules before names go public. Prefer IAP if that is the long-term pattern. | DevOps |  | gcloud compute firewall-rules describe cyberultron-aisecshield-vpc-allow-ssh --project=aisecshield-prod; timeout 3 bash -c "echo >/dev/tcp/34.14.209.218/22" | Must be closed before Cloudflare cutover makes the host easier to find.
MESH-GCP-08 | High | Open | Firewall leftovers | World-open leftover rules: 3389, 8100/8180, 8600 | No | Yes | allow-rdp tcp/3389 0.0.0.0/0; allow-demo-ui tcp/8100+8180 0.0.0.0/0; allow-fireflies-8600 tcp/8600 0.0.0.0/0. Nothing listening on those ports from the internet today (control is 127.0.0.1:8100). | Remove or restrict those rules to operator/VPC ranges. | 8100 not world-open; 8180 not published. No RDP. 8600 not in Mesh SG. | Delete or tighten the three rules so a future bind is not instantly internet-reachable after DNS is public. | DevOps |  | gcloud compute firewall-rules list --project=aisecshield-prod --filter="name~(rdp¦demo-ui¦fireflies)" | Not an active expose today; still must not be internet-open when DNS is public.
MESH-GCP-09 | Medium | Open | Firewall / VPC | allow-internal source CIDR does not match the VPC | No | No | allow-internal sourceRanges 10.10.0.0/24. VPC/subnet is 10.160.0.0/20. Internal traffic currently depends on lower-priority cyberultron-aisecshield-vpc-allow-custom (10.160.0.0/20). | Source CIDR 10.160.0.0/20 (or drop the dead rule if custom covers it). | N/A (AWS SG model). | Correct or delete allow-internal so internal policy is obvious and not a landmine. | DevOps |  | gcloud compute firewall-rules describe allow-internal --project=aisecshield-prod | Dead rule, not a current outage.
MESH-GCP-10 | Medium | Open | Gateway bind | Gateway process still listens on 0.0.0.0:8300 | No | No | ss: 0.0.0.0:8300 docker-proxy. Firewall allow-mesh-gateway-8300 is operator IPs + GCP HC ranges 130.211.0.0/22 and 35.191.0.0/16. :8300 closed from AWS, open from allowlisted ops VM 8.231.115.48. | Keep firewall tight. Stronger: bind gateway to VPC/LB-only (not 0.0.0.0). | Gateway 0.0.0.0:8300 on monolith but SG does not allow internet :8300 (NLB SG only 443). Same pattern. | Do not reopen :8300 to 0.0.0.0/0. Optional compose bind change. | DevOps / platform |  | From a non-allowlisted host: timeout 3 bash -c "echo >/dev/tcp/34.14.209.218/8300" should fail. | Previous “:8300 world-open” finding was a false positive (probed from an allowlisted IP).
MESH-GCP-11 | Medium | Open | ASG / MIG | No MIG; unmanaged IG size 1; deletionProtection false | No | No | No managed instance groups in aisecshield-prod. Unmanaged mesh-firewall-ig size 1, namedPorts http:80 and gateway:8300. Instance deletionProtection false. Secure Boot off, vTPM on. | Enable deletionProtection now. MIG is a later resilience phase unless required for the window. | aimesh-ASG min=max=desired 1, ProtectedFromScaleIn true. aimesh-gateway-asg desired 0 / 0 instances (prod is already a monolith). | Enable deletion protection on mesh-firewall-gcp. MIG optional follow-up. | DevOps |  | gcloud compute instance-groups managed list --project=aisecshield-prod; gcloud compute instances describe mesh-firewall-gcp --zone=asia-south1-c --project=aisecshield-prod --format="yaml(deletionProtection)" | Not a traffic-parity gap vs current AWS (gateway ASG already 0). It is replace-on-failure risk.
MESH-GCP-12 | High | Open | Images / Artifact Registry | Images still pulled from AWS ECR — GCP cannot restart without AWS | No | Yes | Running compose images 935951870001.dkr.ecr.ap-south-1.amazonaws.com/ai-mesh-*:v20260821-cdl-wasa (nginx, gateway, control, workers, mcp-broker, demo). | Mirror tag to Artifact Registry (or equivalent) so a GCP recreate does not depend on AWS ECR. | Same tag on AWS (source of truth today). | Mirror v20260821-cdl-wasa (and future tags) to GAR in aisecshield-prod; point compose at GAR. | DevOps |  | ssh origin: sudo docker ps --format "{{.Image}}" | After DNS cutover, an image pull during incident response still needs the AWS account.
MESH-GCP-13 | Info | Open | Origin TLS | Origin TLS is the baked self-signed cert until Google-managed cert is ACTIVE | No | No | Origin 34.14.209.218:443 issuer/subject CN=zeroshield.ai O=ZeroShield C=IN, 2026-08-21 → 2028-11-23. Browsers need an exception. Chrome HSTS from production often hides Proceed. Bare IP http://34.14.209.218/ returns body “ok” (default vhost). | Public clients use Google-managed cert after cutover. Hosts-file testers keep using 34.14.209.218 with a cert exception until then. | Public names present ACM *.zeroshield.ai. | Include in the cutover runbook (hosts file, HSTS, do not test via raw LB IP). No origin cert change required. | DevOps / QA |  | echo ¦ openssl s_client -connect 34.14.209.218:443 -servername aimeshfirewall.zeroshield.ai ¦ openssl x509 -noout -issuer -subject -dates | Expected. Not a code defect. Tracked so the window runbook is complete.

## Closed — do not rework
ID | Status | Category | Issue (previous claim) | Live result 23 Aug 2026 | What not to do
CLOSED-01 | Closed | HTTP / CDL | Cleartext POST on GCP HTTP frontend is 301 or 411, not 403 | POST/PUT/PATCH/DELETE/OPTIONS with a body → 403 nginx + Via: 1.1 google. GET/HEAD → 301 (same as AWS ALB GET). Empty POST with no Content-Length → Google 411 (AWS ALB still 403 awselb/2.0). | Do not add a second HTTP-method 403 at the URL map unless CDL requires Server: awselb/2.0. Residual 411 without Content-Length is Google proxy behaviour.
CLOSED-02 | Closed | ALB timeout | HTTPS backend timeout 30s vs ALB idle 60s | mesh-firewall-backend timeoutSec is 60. Backend HEALTHY on :80. | Do not retune UI/API timeout. Gateway TCP timeout is still 30s — that is MESH-GCP-05 (open).
CLOSED-03 | Closed | TLS | No SSL policy attached to mesh-firewall-https-proxy | mesh-firewall-ssl-policy MODERN / TLS_1_2 is attached to HTTPS proxy and gateway SSL proxy. | Do not add a policy from scratch. Residual TLS 1.3+PQ alignment is MESH-GCP-06 (open).
CLOSED-04 | Closed | Firewall | tcp/8300 is world-open | allow-mesh-gateway-8300 is operator IPs + GCP health-check ranges only. :8300 closed from AWS; open only from allowlisted 8.231.115.48. Previous finding was a false positive. | Do not open :8300 to 0.0.0.0/0. Keep MESH-GCP-10 (bind hardening) as optional follow-up.
CLOSED-05 | Closed | HTTP URL map | Need Google HTTP frontend to reject mutating methods before HTTPS redirect (was 301 through LB) | HTTP url map mesh-firewall-http-redirect has no redirect rules (name is misleading) and forwards to origin; nginx already 403s mutating methods. Live through LB is 403. | No further URL-map method rule required for 403 status.

## Not issues
ID | Status | Topic | Observation | Why no ticket
N/A-01 | No action | Policy cache version | Gateway /health policy_cache_version is 14 on GCP vs 1035 on AWS; policy_count is 246 on both. vector 14 vs 949. Different agent_id (b02e9852-… vs a48e2e31-…). | Redis generation counters were rebuilt on GCP, not copied. Policy dump is present (246). Do not treat as missing data.
N/A-02 | No action | Postgres data | Both: 49 public tables, 3 orgs (default / zeroshield / testing), 246 policies, 8 users. Events 235533 GCP vs 235520 AWS at last count. | Clone is complete for cutover. Small event delta is drift, not a missing restore.
N/A-03 | No action | Frontend build | Same Last-Modified 21 Aug 2026, etag 6a87cdb8-1d2, security headers (XFO DENY, CSP frame-ancestors none, HSTS 31536000). | No frontend gap for cutover.
N/A-04 | No action | Disk encryption | GCP hyperdisk-balanced 150 GiB, Google-managed encryption (PZI). AWS gp3 150 GiB Encrypted=false, 71G/150G used vs GCP 12G/145G. | GCP is better here. Not an open GCP issue.
N/A-05 | No action | Cloud Armor / WAF | GCP: 0 security policies. AWS: no WAF on ALB, Shield INACTIVE. | Parity, not a GCP regression. Optional hardening later; not in this open list.

## Cutover checklist
# | Phase | Check | Pass criteria | Owner | Done?
1 | Before DNS | SSH locked to three operator IPs | tcp/22 not reachable from a non-operator host | DevOps
2 | Before DNS | Remove/tighten 3389, 8100/8180, 8600 rules | Rules gone or not 0.0.0.0/0 | DevOps
3 | Before DNS | Cert strategy agreed (split certs vs move all three names together) | Written plan; MESH-GCP-03 closed or accepted | DevOps
4 | Before DNS | Memorystore resized (or risk accepted in writing) | Size comparable to r7g.xlarge or signed waiver | DevOps
5 | Before DNS | Gateway backend timeout raised | timeoutSec ≥ 60 (prefer 300–350) | DevOps
6 | Before DNS | ECR images mirrored to Artifact Registry (or waiver) | GCP recreate does not require AWS ECR | DevOps
7 | Before DNS | Enable instance deletion protection | deletionProtection true on mesh-firewall-gcp | DevOps
8 | Before DNS | Rollback CNAMEs documented | Current ALB/NLB CNAME targets saved | DevOps / DNS
9 | During window | Cloudflare: firewall+backend A 34.110.253.110 | dig matches | DNS owner
10 | During window | Cloudflare: gateway A 136.68.95.231 | dig matches; not 34.110.253.110 | DNS owner
11 | During window | Wait for mesh-firewall-cert ACTIVE on all three names | gcloud domainStatus all ACTIVE | DevOps
12 | After cert | https://aimeshfirewall.zeroshield.ai/login → 200 | Google-managed cert, not self-signed | QA / DevOps
13 | After cert | https://aimeshbackend.zeroshield.ai/api/health/ → 200 | {"status":"ok"} | QA / DevOps
14 | After cert | https://aimeshgateway.zeroshield.ai/health → 200 | policy_count 246; SSL-proxy path (not nginx UI LB) | QA / DevOps
15 | After cert | https://aimeshgateway.zeroshield.ai/openapi.json → 401 | Auth still required | QA / DevOps
16 | After cert | POST http://aimeshfirewall…/api/auth/token/ → 403 | Not 301 | QA / DevOps